| PROJECT NAME | Conference Room Management System | | | PROJECT MANAGER |  |
| --- | --- | --- | --- | --- | --- |
| PROJECT DELIVERABLE | A fully working conference room management system where users are able to book rooms and admin is able to manage conference rooms | | | | |
| SCOPE STATEMENT | User should be able to login and book rooms while admin should be able to add rooms, manage bookings and create new admin accounts | | | | |
| START DATE | 24/08/2022 | END DATE | 20/11/2022 | OVERALL PROGRESS | 100% |

| **TASK NAME** | **ASSIGNED TO** | **START  DATE** | **END  DATE** | **DURATION**  in days |
| --- | --- | --- | --- | --- |
| **SPRINT 1** |  | 24/08 | 20/09 | 28 |
| Building Login Page frontend | Sanath Sreekanth | 24/08 | 30/08 | 7 |
| Creating database and integrating login page frontend with database | Sanmat | 31/08 | 13/09 | 14 |
| Building security features to secure database against unauthorized access | Shamith V S | 13/09 | 20/09 | 7 |
| **SPRINT 2** |  | 21/09 | 18/10 | 28 |
| Displaying different types of conference rooms available | Sampreeth Nadig | 21/09 | 27/09 | 7 |
| Building Room booking page and integrating with backend | Shamith V S | 21/09 | 04/10 | 14 |
| Building Payments page and integrating with backend | Sanath Sreekanth | 05/10 | 18/10 | 14 |
| **SPRINT 3** |  | 19/10 | 16/11 | 28 |
| Enabling manager to add new manager accounts with manager privileges and storing new account information in database | Sanmat | 19/10 | 25/10 | 7 |
| Enabling manager to add new room types | Sampreeth Nadig | 25/10 | 09/11 | 14 |
| Creating manager dashboard to manage bookings | Shamith V S | 02/11 | 16/11 | 14 |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **TaskID** | **Task Name** | **Start**  **Week** | **End**  **Week** |  | **WK01** | **WK02** | **WK03** | **WK04** | **WK05** | **WK06** | **WK07** | **WK08** | **WK09** | **WK10** | **WK11** | **WK12** | **WK13** | **WK14** | **WK15** |
| 01 | **SPRINT1** | WK01 | WK04 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 01.01 | Login Page | WK01 | WK01 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 01.02 | Creating database and integrating login page | WK02 | WK03 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 01.03 | Securing Database | WK04 | WK04 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 02 | **SPRINT2** | WK05 | WK08 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 02.01 | Room Availability Page | WK05 | WK05 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 02.02 | Room Booking Page | WK05 | WK06 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 02.03 | Payments Page | WK07 | WK08 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 03 | **SPRINT3** | WK09 | WK12 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 03.01 | Allowing managers to addnew manager acco | WK09 | WK09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 03.02 | Allowing managers to add new room types | WK10 | WK11 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 03.03 | Managing bookings page | WK11 | WK12 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |